## SUBCONTRACTOR BID ANALYSIS CASE STUDY

### Drywall & Metal Framing (CSI Division 09) - Classroom Renovation - 3,000 sq ft (Simulated)

## 1. Personal Introduction

The purpose of this case study was to deepen my understanding of US subcontracting and preconstruction decision-making, specifically focusing on scope levelling, CSI-based comparison, cost-risk evaluation, and selection criteria used by General Contractors (GCs).

Having worked in India on projects involving vendor coordination and quantity verification, I understood basic bidding dynamics. However, US subcontracting uses more formal structures, including

- CSI divisions,

- Detailed inclusion/exclusion lists,

- Risk-based evaluation,

- Schedule-driven manpower assessments, and

- Quality/performance specifications (fire rating, STC ratings, UL assemblies).

I wanted to learn how a GC chooses not the cheapest, but the best-value subcontractor, especially for interior renovation projects, where coordination, acoustic performance, and fire safety are critical.

This case study simulates the complete bid levelling and subcontractor evaluation process for a drywall and framing package in a classroom renovation project.

# 2. Case Scenario: Classroom Renovation Overview

### Project Name: Midtown Community College - Classroom Renovation (Interior TI)

### Project Size: 3,000 sq ft (two classrooms + corridor improvements)

### Project Goals:

- Improve acoustic performance between classrooms

- Meet updated fire-rated corridor requirements (1-hour separation)

- Modernize interior partitions

- Prepare space before semester start

### Existing Constraints:

- Renovation in an active campus environment

- Limited working hours due to student movement

- Low ceiling height causing MEP coordination challenges

- Strict fire marshal inspection process

### Trade package under review:

Drywall & Metal Framing (CSI Division 09) - one of the most commonly subcontracted scopes in US construction.

# 3. Scope of Work (CSI Breakdown)

### Metal Stud Framing (CSI 09 22 16)

- Non-load bearing walls

- Corridor partition studs

- Bulkheads and soffit framing

- Blocking/backing for AV equipment

### Gypsum Board Installation (CSI 09 29 00)

- 5/8" regular gypsum board

- 5/8" Type X (fire-rated) gypsum board

- Double-layer boarding for storage rooms

### Acoustic Assemblies (CSI 09 29 49)

- STC 45–50 partitions

- Acoustic sealants around penetrations

- Putty pads for outlet acoustics

### Shaft-wall Assemblies (CSI 09 21 16)

- For mechanical chases (UL-rated assembly)

### Finishing (CSI 09 29 10)

- Joint taping, mudding, sanding

- Level 4 finish

- Surface preparation for paint

# 4. Project Constraints & Risks

This trade directly affects:

### a) Schedule

Drywall sits on the critical path, ahead of:

- MEP trim-out

- Painting & finishes

- Ceiling grid installation

Delays here cascade into multiple downstream trades.

### b) Fire Safety

Incorrect installation can cause inspection failures, delaying occupancy.

### c) Acoustic Performance

Educational spaces require quiet classrooms; improper installation impacts STC ratings.

### d) Coordination

MEP penetrations must be installed before board closure.

### e) Work Environment

Renovation occurs while other classrooms remain active; i.e., noise limits and sequencing challenges.

# 5. Summary of Subcontractor Bids

Three subcontractors submitted proposals:

## Bidder A: Alpha Inc.  Bid Price: $152,300

- Crew Size: 6

- Schedule: 6 weeks

- Inclusions: Standard gyp board, Type X board, metal studs

- Exclusions:

  - STC-rated acoustic wall assemblies

  - Shaft wall systems

  - Acoustical sealants

  - Fire caulking

## Bidder B: Intam & Co.

- Bid Price: $169,800

- Crew Size: 9

- Schedule: 5 weeks

- Inclusions:

  - Full metal framing

  - Type X assembly

  - STC 45–50 partitions

  - Shaftwall installation

  - All acoustical sealants

  - Level 4 finish

- Exclusions: None

## Bidder C: Beta Ltd

- Bid Price: $184,200

- Crew Size: 12

- Schedule: 4.5 weeks

- Inclusions: Full framing and board

- Exclusions:

  - Level 4 finishing

  - Fire stopping materials

Key Observations:

| Bidder A | Bidder B | Bidder C |
| --- | --- | --- |
| ## Lowest Price, Highest Risk | Middle Price, Most Complete | Highest Price, Fastest Schedule |
| Achieves low price through major scope exclusions. Could result in multiple change orders. | Most complete, technically aligned, schedule-compliant | Delivers work quickly but shifts key risks back to GC |

# DETAILED CSI SCOPE ANALYSIS

# 6. CSI based scope comparison table

| CSI Scope Item | Bidder A | Bidder B | Bidder C | GC Evaluation Notes |
| --- | --- | --- | --- | --- |
| 09 22 16 Metal Stud Framing | Included | Included | Included | All bidders compliant; no scope variance. |
| 09 29 00 Gypsum Board | Included | Included | Included | Full alignment; standard & Type X board included by all. |
| 09 29 49 Acoustic Wall Assemblies (STC 45–50) | Excluded | Included | Included | A excludes required STC partitions major performance & spec compliance risk. |
| Acoustical Sealants / Putty Pads | Excluded | Included | Included | Required for STC rating; omission creates acoustic failure risk. |
| 09 21 16 Shaft wall Assemblies (UL Rated) | Excluded | Included | Included | High-value system; exclusion in A indicates significant change-order exposure. |
| 09 29 10 Level 4 Finish | Included | Included | Excluded | C excludes finishing, shifting labor & cost burden back to GC. |
| Fire stopping Materials | Partial | Included | Excluded | Required for inspection and occupancy; C’s exclusion is a compliance risk. |
| MEP Coordination Allowance | Limited | Inclusive | Inclusive | Impacts sequencing, rework, and inspection efficiency. |

Observation:
Bidder B is the only bidder with a fully complete and code-compliant scope.

# 7. Scope Gaps & Risk Identification

## Bidder A: High Risk

- Critical assemblies missing (STC, shaft wall)

- No acoustical sealants i.e., STC failure

- High likelihood of change orders

- Slowest schedule (6 weeks, misses deadline)

- Not acceptable for a campus timeline

## Bidder B: Low Risk

- No scope exclusions

- Crew size adequate

- Compliant with all fire and acoustic requirements

- Predictable cost

## Bidder C: Medium Risk

- Missing Level 4 finish can cause immediate cost add

- Missing fire stopping, which will cause inspection failure

- Strong manpower but unnecessary speed premium

# 8. Weighted GC Evaluation Matrix

| Criteria | Weightage | A | B | C |
| --- | --- | --- | --- | --- |
| Scope Completeness | 35% | 1 | 5 | 3 |
| Cost Competitiveness | 20% | 5 | 3 | 2 |
| Schedule Reliability | 20% | 2 | 4 | 5 |
| Change Order Risk | 15% | 1 | 5 | 3 |
| Vendor Reliability | 10% | 3 | 4 | 3 |
| Final Score |  | 12 | 21 | 16 |

Legend (1-5 Scale)

5 = Excellent / Complete / Lowest Risk

4 = Strong / Minor Issues

3 = Acceptable / Meets Requirements

2 = Weak / Gaps Present

1 = Poor / High Risk / Major Exclusions

Observation: Bidder B outperforms both competitors by a wide margin.

# 9. Risk Heat Map (Text Analysis)

Risk categories were evaluated using Probability (P) and Impact (I):

| Risk Item | P | I | Rating | GC Note |
| --- | --- | --- | --- | --- |
| Missing STC assemblies (A) | High | High | Severe | Fails acoustic requirements; major rework and performance risk. |
| Missing shaft wall (A) | Medium | High | Severe | Code critical assembly omitted; likely change order and delay. |
| Level 4 finish excluded (C) | Medium | Medium | Moderate | Adds cost and coordination effort back to GC. |
| Crew too small (A) | High | Medium | Moderate | Unlikely to meet 5-week schedule; delays downstream trades. |
| Fire stopping omitted (C) | Low | High | Moderate | Inspection risk; may delay occupancy. |
| A. sealants excluded (A) | High | Low | Low | Impacts STC performance; minor rework but accumulates cost. |

Observation:

- Bidder A carries unacceptable red-zone risks.

- Bidder C carries several moderate risks.

- Bidder B carries none.

# 10. Final Recommendation

### Award Contract To: Bidder B

Rationale:

Bidder B is the recommended subcontractor due to its fully complete scope with zero exclusions, which significantly reduces change-order exposure and minimizes risk to the GC. The bidder’s 5-week schedule aligns precisely with the campus renovation timeline, ensuring classrooms are ready for the start of the semester. Bidder B includes all critical fire-rated and acoustic assemblies, supporting compliance with code requirements and design intent. Although not the lowest-priced option, it delivers the strongest value by offering the lowest overall project risk. The completeness of Bidder B’s scope also supports smoother inspections, more efficient MEP coordination, and predictable field execution—making it the most reliable and cost-effective choice.

### Why not Bidder A?

- Scope exclusions threaten fire safety, acoustics, and schedule.

- Would create numerous change orders, increasing total project cost.

### Why not Bidder C?

- Higher cost does not create proportional value.

- Missing fire stopping and finishing → additional GC management burden.

# 11. Key Takeaways & Reflection

This simulation strengthened my understanding of:

- CSI-Based Scope Reading

### I learned how to interpret subcontractor scope sheets using CSI divisions and identify missing assemblies.

- Bid Levelling

### Comparing inclusions, exclusions, manpower, and schedule helped me practice GC-style evaluation.

- Risk Management

### Understanding how exclusions affect schedule and budget improved my preconstruction thinking.

- Value-Based Decision Making

### I learned how GCs choose the best overall value, not the lowest price.

- Subcontractor Coordination Awareness

Recognizing how drywall sequencing impacts MEP trades, inspections, and occupancy deadlines.

This case study reflects my ability to think like a Project Engineer, Preconstruction Intern, Estimating Intern, or Field Engineer, and demonstrates readiness for GC-level analytical tasks.